## Sheet 1
Table 1
| Theme 1 | Building Capacity, Skills & Understanding
| Action | Description | Lead Organisation | Lead Name | Timescale | Measure | RISK | How might this be achieved?
| 1.1 | Build on the guidance and support available to community groups, link workers and health practitioners in our toolkit and promote these further | NHS | Helen Perkins/Sophie Isaacson | Sept 24 | Number of promotion events/activities | People won't use the resources without support. | Through provision of online toolkits, videos and printed guidance. | GOOD PROGRESS
| 1.2 | Provide person-centred training tools to those referring in to nature-based health improvement programmes and interventions | NHS | Helen Perkins/Sophie Isaacson | Sep 24 | Number attending relevant courses | Sign-up to TURAs may put people off | Promote NHS training prospectus to staff Invite people to sign up to TURAS | GOOD PROGRESS
| 1.3 | Apply Behaviour Change and Quality Improvement Methodologies to our Communications Work. Extend engagement work to include NHS Greenspace initiatives | NHS | Kate Thomson/Sophie Isaacson | Sep 24 | Continue with current measures web-hits/downloads/social media | Risk of not reaching the right audiences | Through Communications Sub-Group. Use nationally recognised tools around behaviour and engagement. | GOOD PROGRESS
| 1.4 | Review our definitions and language and work with stakeholders to ensure consistency of approach | ALL | Helen Perkins/Sophie Isaacson | Sep 24 | Published Definitions | Risk of confusion between different initiatives. Public not on board. Terminology may be offputting to some. | Review current guidance on definitions and share with aprtnership and wider | COMPLETE
| Theme 2 | Adding Value Through Collaborative Working
| Action | Description | Lead Organisation | Lead Name | Timescale | Measure | RISK | How might this be achieved?
| 2.1 | Ask Highland stakeholders to commit to a Green Health Charter and report progress against this. | NHS/ ALL | Helen Perkins/Ailsa Villegas | Sep 24 | Number organisations signed up. | Signing up will be easy. Getting them to report will be harder. | 1. Invite Signatories to present their progress to HGHP on a rotating basis. 2. Have signatories demonstrate their commitment on their websites and public facing media. 3. Start with HGHP members then expand to Community Planning Partners. 4. Ask HGHP to feedback what they think would be valuable to know in reporting and find common ground where progress can be fed back through existing monitoring systems. 5. Include a prevention focus not just intervention. 6. Commit to raise awareness within internal orgs. | ONGOING
| 2.2 | Establish thematic sub-groups of community partnerships that address nature, climate and health and a network of shared practice among these. | CP Chairs/ HC Community Planning Officers/NHS/HEF | Ailsa Villegas/Caroline Vawdrey | Sep 24 | 1. Community Action Plans developed 2.Who is represented in each locality 3. Emerging Priorities | Getting the right people represented on the groups. Some CP's not very active. Rotating chairs. Competing priorities. Lack of duning to support. | Link to Statutory local place plans. 2. Create online seminars and have network events, seek funding for HEF to lead on the delivery of this work. 3. Field trips to see green health in action 4. Include the Countryside rangers in these groups. 5. NHS/HLH have reps on each CP and can report back progress. 6. Invite CP officers to join HGHP. 7. Use and creation of tools. | ONGOING
| 2.3 | Make links with all relevant strategic groups and committees in Highland. Seek new opportunities to embed Green Health Principals into new regional plan development plans. | All partners | Helen Perkins | Sep 24 | Number Strategy groups presented to/linked in with. 2. Continue to monitor the number of PPS that mention Green HEalth | Risk of becoming Inverness focused. 2. Risk of paying lip service and no action 3. Delayed action. 4. Missing key groups 5. Changing landscape of committees and keeping on top of this. | 1. HC Climate Change Committee - link to Net Zero Strategy.2. HC H&SC Committee. 3. Learning for Sustainability - Education. 4. Communities and Place. 5. Env & Economic Development - link to NP4 (include this in logic model) 6. Highland Biodiversity Action Plan 7. make links with community resilience teams. 8 make links with the outdoor volunteering group.9. CNPA Board 10. HLH Board 11. NHS Board 12. Local Outdoor Access Forums 13. Ask HGHP members where we are currently represented - make this a priority for next HGHP. 14. Find our high level champions | ONGOING
| 2.4 | Continue to gather and build on the shared evidence base, including qualitative case studies that demonstrate the impact. Link with new areas such as use of pharmaceuticals, climate change and blue health | All partners | Helen Perkins/Sophie Isaacson |  |  | Know who the audience is for. Risk they aren't read. | 1. Are we asking the right people for case studies? Work with our adult learning centres. 2. Evaluate the process as well as the outcomes 3. Learn from best practice including social enterprise. 4. Short term outcome who has examples? 5. Speak with Highland Adapts for climate stories and add a public health spin. 6. Ask HTSI Forums.7. Link this to the shared learning networks. | ONGOING
| Theme 3 | Embedding & Integrating
| Action | Description | Lead Organisation | Lead Name | Timescale | Measure | RISK | How might this be achieved?
| 3.1 | HGHP Members to continue to promote workplace wellbeing initiatives around Green Health | All partners |  | ongoing | Key messages of HGHP integrated into partners internal communications to staff; Partner organisations continue to support and build on green health initiatives on offer to staff; Green Health valued as key to achieving climate/sustainability strategies and targets; Partnership leadership teams actively promote and engage with green health in the workplace, e.g. health walks, daily moments in nature, outside meetings, Staff of partner organisations report positive culture and permission around incorporating green health into the workplace. | Communication doesn't necessarily lead to behaviour change and measuring impact of comms is hard; Without someone coordinating could lose momentum. | 1.Outline key messages in communications plan, messages relating to individuals and organsations e.g. nature connection is good for your mental health and wellbeing, and people who are connected to nature are more likely to engage in pro-environmental behaviours;2. Embed key messages within partners internal communications via heads of HR/comms team; 3.Identify and share with partners communications teams key yearly initiatives (green health week, climate week, May walking month, Paths for All Step Count Challenge);4 Include workplace wellbeing in the Highland Green Health Charter;4. Link in with healthy working lives award, does Green Health feature?- encourage all partner organisations to pay staff for a volunteer day a year, NatureScot staff programme as example. Paths for All workplace walking tools/awards promoted to all partner HR teams.5. Link with Active Highland Strategy Group and their messaging. | PARTIAL PROGRESS
| 3.2 | Continue to work with our higher education institutes through student placements, graduate and post graduate research and job placement opportunities. | ALL | Dan Jenkins/ Imogen Furlong | Ongoing | Number of Green Health related placememts/ course uptake | Capacity to coordinate; Communications lead needed; Not getting buy- in from stakeholders | 1.HLH Green Leadership Award. 2.Abn Sustainable Medicine students.3. Work with Andrew Dallas Realistic Medicine course; 5.Share case studies and success stories of routes to employment and positive experiences; 6.Promote Green Health opportunities through the Modern Apprenticeship scheme with HC. 7.Work with High Schools, partners and green health providers to promote green health opportunities for work experience pupils/student placements? | PARTIAL PROGRESS
| 3.3 | Ensure Greenspace & Green Infrastructure projects in Highland work to tackle health inequalities through the promotion of connection to nature | HC & NHS | Katy Paterson & Matthew Hilton; and Kate Thomson |  | Greenspace infrastructure project placement consider impact on health inequalities e.g. target areas of socio-economic disadvantage, greening these areas first. | Funding. For example limits of annual funding for community projects- need to be ready to go, lack of funding for maintenance and funding opportunities for biodiversity/climate action not always well related to reducing health inequalities; Readiness of community groups to make use of short-term funding. | Communicating importance of biodiversity for health and wellbeing to public, stakeholders & funders; Support to community planning partnerships to coordinate networks and community groups; Community engagement events attached to greenspace improvement sites e.g. HC 10 sites for biodiversity as per meadow mosaic project model; Share learning around tools such as the tree equity tool; and NHS hospital greenspace projects to be co-developed with local communities with access a key priority. | PARTIAL PROGRESS
| 3.4 | Partners integrate and embed key messaging throughout the delivery of their work -replacing a dedicated green health work stream. | All partners; HEF | All partners comms teams and Caroline Vawdrey | Ongoing | Partners internal and external comms regularly include messaging around benefits of green health and relevant opportunities. | Lack of coordination if no funding to continue communications and engagement officer post; HEF funding year to year. | Outline key messages in communications plan; Share communications plan with partners communications teams and partners to encourage encorporating messages into relevant organisation comms plans; Encourage green health to be incorporated into partners external communications/newsletters; Include in Highland Green Health Charter; and HEF to continue to promote HGHP key messages and opportunities to members via newsletter and events. | ONGOING
| Theme 4 | Sustainable Funding
| Action | Description | Lead Organisation | Lead Name | Timescale | Measure | RISK | How might this be achieved?
| 4.1 | Work to develop a funding package to support communities in green health initiatives in 2023-2024 with continued focus on Sustainability (Green Health Small Grant Fund) | All | Matthew Hilton for some initial scoping/contact making; liaise with Alison Grant. Katie Paterson key link for Nature Restoration Fund | Jan 2024 | Use exisisting feedback and evaluation process. | Funding pots not available. This may mean delivery partners in the community drift off; valuable evidence gathering around local approaches may be lost | Ward/locality based funds; Coastal Communities Fund (could be multi-year)?; Nature Restoration Fund (this needs to be spent by the end of the financial year).HC to check locality funds that might be available to apply for | NO PROGRESS
| 4.2 | Work collaboratively to secure ongoing funding to support nature-based health improvement initiatives and enhance our greenspaces, including unlocking Capital funding. | HC | Matthew H check lead for funds; Alison Grant manages ward managers. Katie Paterson key link for Nature Restoration Fund | April 2024 onwards | long term funding established; match funding sources identified; | Momentum of work built up so far may be lost; capacity within communities to deliver sustainable Nature-based Social Prescribing destinations may be lost | Ward/locality based funds; Coastal Communities Fund (could be multi-year)?; Nature Restoration Fund - could this be utilised as time-bound match funding for larger projects | LIMITED PROGRESS
| 4.3 | Co-design funding programmes with the third sector through delivery of a funders forum. | HTSI | Mhairi Wylie |  | Engagement levels from funders; resultant funding framework | Increasing competition for diminishing pots of funding | Development of the structure supported by input from HGHP members. Invitations to funders forum go through well-considered targetting. | NO PROGRESS
| 4.4 | Work to promote and encourage social enterprise around Green Health service delivery in Highland. | NHS/HIE | Keith Masson |  | Examples of social enterprise identified and learning shared; new SE organisations come into existence | Potential for widening inequalities if provision of services becomes skewed towards recipients with greater resources | Green Health Development Fund could help?; climate mitigation funding might be an option for some organisations | NO PROGRESS